## Template Visual Inspection
Employer | Project | Module | Contractor | Discipline | Report No | Date | Drawing No | Description | Requested By | Document Reference No | Drawing Weldmap | Item /Joint no | Type Of Weld | WPS | Cons / Lot No | Weld Process RH | Weld Process FC | Welder RH | Welder FC | Thickness | Length | Weld Completion Date | Inspection Result ACC REJECT PENDING | NDE MT Check : 1 Uncheck : 0 | NDE PT Check : 1 Uncheck : 0 | NDE UT Check : 1 Uncheck : 0 | NDE RT Check : 1 Uncheck : 0 | Remarks
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | HAISYAM | WQT-STR-SOF-0150 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | ANDIKA ADIPATI | WQT-STR-SOF-0151 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | HASAN SYAH | WQT-STR-SOF-0152 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | MUSTAMAN | WQT-STR-SOF-0153 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | ZUL AIDI | WQT-STR-SOF-0154 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | ALIMUDDIN | WQT-STR-SOF-0155 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | SAIDAN | WQT-STR-SOF-0156 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | AZMAN | WQT-STR-SOF-0157 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | ABDUL ROSIP SIAGIAN | WQT-STR-SOF-0158 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | REKY PRANTO PANGGABEAN | WQT-STR-SOF-0159 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | HOLMES SIMANGUNSONG | WQT-STR-SOF-0160 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | PAISAL HARAHAP | WQT-STR-SOF-0161 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | SAHAT PURBA | WQT-STR-SOF-0162 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | SYAFROYONI | WQT-STR-SOF-0163 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | TAUFIK | WQT-STR-SOF-0164 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -
RWE | SOFIA | - | SEMBCORP MARINE | STRUCTURAL | WQT-VIS-STR-SOF-0015 | 2021-08-31 | - | STRUCTURE | ARI AFRIZA | - | RYAN ARISTU | WQT-STR-SOF-0165 | BW | SO-STR-SMFC-07 | - | FCAW GS - 4G | FCAW GS - 4G | HIRE | HIRE | 25 | 300 | 2021-08-31 | - | 0 | 0 | 1 | 0 | -